## Schedule
To-Do List & Schedule
|  | 2016-05-31 |  | complete | on going | plan | delay
168
| Event | Level 1 | Level 2 | Assign | Start (Plan) | End (Plan) | Actual (Hour) | Status | time axis 2016-05-09 to 2016-06-25
| planning | making the plan for project schedule |  | All | 2016-05-09 | 2016-05-27 | 12 | Complete | 2016-05-09: 1; 2016-05-10: 1; 2016-05-11: 2; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 1; 2016-05-25: 1; 2016-05-26: 1; 2016-05-27: 0
|  | making the partitioning the works |  | All | 2016-05-09 | 2016-06-03 | 17 | Complete | 2016-05-09: 1; 2016-05-10: 1; 2016-05-11: 2; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 1; 2016-05-25: 1; 2016-05-26: 1; 2016-05-27: 0; 2016-05-31: 5
|  | organizing the team and assigning roles |  | All | 2016-05-09 | 2016-05-27 | 17 | Complete | 2016-05-09: 1; 2016-05-10: 1; 2016-05-11: 2; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 1; 2016-05-25: 1; 2016-05-26: 1; 2016-05-27: 0; 2016-05-31: 5
|  | making a risk assessment |  | All | 2016-05-09 | 2016-06-03 | 8 | Complete | 2016-05-09: 1; 2016-05-10: 1; 2016-05-11: 2; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 0; 2016-05-24: 0; 2016-05-25: 0; 2016-05-26: 0; 2016-05-27: 0
|  | create the key mileston and detaile task lists |  | All | 2016-05-09 | 2016-06-03 | 12 | Complete | 2016-05-09: 1; 2016-05-10: 1; 2016-05-11: 2; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 0; 2016-05-24: 2; 2016-05-25: 2; 2016-05-26: 0; 2016-05-27: 0
|  | setup up how to write down the time logs. |  | All | 2016-05-09 | 2016-05-27 | 12 | Complete | 2016-05-09: 1; 2016-05-10: 1; 2016-05-11: 2; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 1; 2016-05-25: 1; 2016-05-26: 1; 2016-05-27: 0
|  | Decide how tracking the team progress. |  | All | 2016-05-09 | 2016-05-27 | 12 | Complete | 2016-05-09: 1; 2016-05-10: 1; 2016-05-11: 2; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 1; 2016-05-25: 1; 2016-05-26: 1; 2016-05-27: 0
| Requirement | Figure out the contexts(market, organization, business and technical) |  | All | 2016-05-09 | 2016-05-27 | 12 | Complete | 2016-05-09: 0; 2016-05-10: 0; 2016-05-11: 1; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 2; 2016-05-17: 1; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 2; 2016-05-25: 3; 2016-05-26: 1; 2016-05-27: 0
|  | List up the funtional requirement |  | All | 2016-05-09 | 2016-05-27 | 12 | Complete | 2016-05-09: 0; 2016-05-10: 0; 2016-05-11: 1; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 2; 2016-05-25: 3; 2016-05-26: 1; 2016-05-27: 0
|  | List up quality attribute |  | All | 2016-05-11 | 2016-05-27 | 12 | Complete | 2016-05-09: 0; 2016-05-10: 0; 2016-05-11: 1; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 2; 2016-05-25: 3; 2016-05-26: 1; 2016-05-27: 0
|  | make use case in detail |  | All | 2016-05-12 | 2016-05-27 | 11 | Complete | 2016-05-09: 0; 2016-05-10: 0; 2016-05-11: 0; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 2; 2016-05-17: 1; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 2; 2016-05-25: 3; 2016-05-26: 1; 2016-05-27: 0
|  | make scenarioes of the quality attribute |  | All | 2016-05-12 | 2016-05-27 | 11 | Complete | 2016-05-09: 0; 2016-05-10: 0; 2016-05-11: 0; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 1; 2016-05-17: 2; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 2; 2016-05-25: 3; 2016-05-26: 1; 2016-05-27: 0
|  | List up the constraints(business, technical) |  | All | 2016-05-09 | 2016-05-27 | 8 | Complete | 2016-05-09: 0; 2016-05-10: 0; 2016-05-11: 1; 2016-05-12: 0; 2016-05-13: 0; 2016-05-16: 2; 2016-05-17: 1; 2016-05-18: 1; 2016-05-19: 0; 2016-05-20: 0; 2016-05-23: 1; 2016-05-24: 2; 2016-05-25: 0; 2016-05-26: 0; 2016-05-27: 0
| design | 1st decomposition |  | All | 2016-05-31 | 2016-06-03 | 10 | On Going | 2016-05-09: 0; 2016-05-31: 10
Facility Controller design
|  |  | Sensor/Servo/LED control design | Charles | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | wifi control design | Charles | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | Facility-Controller protocol design | Charles | 2016-06-01 | 2016-06-17 | 0 | On Going
Sure-park web client design
|  |  | Reservation UI design | Namjin | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | Monitoring UI design | Namjin | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | Management UI design | Namjin | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | Log in UI/Sign up design | Namjin | 2016-06-01 | 2016-06-17 | 0 | On Going
Sure-park web server design
|  |  | DB transaction | Jack | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | Web server-Controller protocol design | Jack | 2016-06-01 | 2016-06-17 | 0 | On Going
controller design
|  |  | DB transaction | Heon | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | Facility-Controller protocol design | Joan | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | Web server-Controller protocol design | Heon | 2016-06-01 | 2016-06-17 | 0 | On Going
|  |  | Reservation Management | Joan | 2016-06-01 | 2016-06-17 | 0 | On Going
| Implementation/Unit test | Facility Controller Implementation
|  |  | Sensor/Servo/LED control Implementation | Charles | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | WIFI control Implementation | Charles | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | Facility-Controller protocol Implementation | Charles | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | unit test | Charles | 2016-06-06 | 2016-06-23 | 0 | Plan
Sure-park web client Implementation
|  |  | Reservation UI Implementation | Namjin | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | Monitoring UI Implementation | Namjin | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | Management UI Implementation | Namjin | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | Sign up/Log in Implementation | Namjin | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | unit test | Namjin | 2016-06-06 | 2016-06-23 | 0 | Plan
Sure-park web server Implementation
|  |  | DB transaction | Jack | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | Web server-Controller protocol Implementation | Jack | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | unit test | Jack | 2016-06-06 | 2016-06-23 | 0 | Plan
controller Implementation
|  |  | DB transaction | Heon | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | Facility-Controller protocol Implementation | Joan | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | Web server-Controller protocol Implementation | Heon | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | Reservation Management | Joan | 2016-06-06 | 2016-06-23 | 0 | Plan
|  |  | unit test | Heon/Joan | 2016-06-06 | 2016-06-23 | 0 | Plan
| Testing | Run integration test |  | All | 2016-06-15 | 2016-06-23 | 0 | Plan
documentation
|  | time log tracking |  | Namjin | 2016-05-09 | 2016-06-23 | 2 | On Going | 2016-05-11: 0.2; 2016-05-16: 0.2; 2016-05-17: 0.2; 2016-05-18: 0.2; 2016-05-23: 0.2; 2016-05-24: 0.2; 2016-05-25: 0.2; 2016-05-26: 0.2; 2016-05-30: 0.2; 2016-05-31: 0.2
|  | Architectural design doc |  | Joan | 2016-06-15 | 2016-06-23 | 0 | Plan

## Schedule old
To-Do List & Schedule
2016-05-31
| Event | Task | Assign | Start (Plan) | End (Plan) | Period | Status | 2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20 | 2016-05-21 | 2016-05-22 | 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27 | 2016-05-28 | 2016-05-29 | 2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03 | 2016-06-04 | 2016-06-05 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-11 | 2016-06-12 | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17 | 2016-06-18 | 2016-06-19 | 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24 | 2016-06-25
| planning | making the plan for project schedule | All | 2016-05-09 | 2016-05-27 | 15 | Complete | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| planning | making the partitioning the works | All | 2016-05-09 | 2016-06-03 | 20 | Complete | 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All; 2016-05-28: All; 2016-05-29: All; 2016-05-30: All; 2016-05-31: All; 2016-06-01: All; 2016-06-02: All; 2016-06-03: All
| planning | organizing the team and assigning roles | All | 2016-05-09 | 2016-05-27 | 15 | Complete | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| planning | making the plan to efficiently communicate among the team and with the mentors | All | 2016-05-09 | 2016-05-27 | 15 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| planning | making a risk assessment | All | 2016-05-09 | 2016-06-03 | 20 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All; 2016-05-28: All; 2016-05-29: All; 2016-05-30: All; 2016-05-31: All; 2016-06-01: All; 2016-06-02: All; 2016-06-03: All
| planning | create the key mileston and detaile task lists | All | 2016-05-09 | 2016-06-03 | 20 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All; 2016-05-28: All; 2016-05-29: All; 2016-05-30: All; 2016-05-31: All; 2016-06-01: All; 2016-06-02: All; 2016-06-03: All
| planning | setup up how to write down the time logs. | All | 2016-05-09 | 2016-05-27 | 15 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| planning | Decide how tracking the team progress. | All | 2016-05-09 | 2016-05-27 | 15 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| Requirement | Figure out the contexts(market, organization, business and technical) | All | 2016-05-09 | 2016-05-27 | 15 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| Requirement | List up the funtional requirement | All | 2016-05-09 | 2016-05-27 | 15 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| Requirement | List up quality attribute | All | 2016-05-11 | 2016-05-27 | 13 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| Requirement | make use case in detail | All | 2016-05-12 | 2016-05-27 | 12 | On Going | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| Requirement | make scenarioes of the quality attribute | All | 2016-05-12 | 2016-05-27 | 12 | Complete | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| Requirement | List up the constraints(business, technical) | All | 2016-05-09 | 2016-05-27 | 15 | Complete | 2016-05-16: All; 2016-05-17: All; 2016-05-18: All; 2016-05-19: All; 2016-05-20: All; 2016-05-21: All; 2016-05-22: All; 2016-05-23: All; 2016-05-24: All; 2016-05-25: All; 2016-05-26: All; 2016-05-27: All
| Desgin | Design the architecture for Arduino |  | 2016-05-30 | 2016-06-17 | 15 | Plan | 2016-05-30: 0; 2016-05-31: 0; 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0
| Desgin | Design the architecture for context server. |  | 2016-05-30 | 2016-06-17 | 15 | Plan | 2016-05-30: 0; 2016-05-31: 0; 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0
| Desgin | Desgin the DB schema |  | 2016-05-30 | 2016-06-17 | 15 | Plan | 2016-05-30: 0; 2016-05-31: 0; 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0
| Desgin | Desgin the back-end web framework. |  | 2016-05-30 | 2016-06-17 | 15 | Plan | 2016-05-30: 0; 2016-05-31: 0; 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0
| Desgin | Design the front-end web service. |  | 2016-05-30 | 2016-06-17 | 15 | Plan | 2016-05-30: 0; 2016-05-31: 0; 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0
| Implementation | Implement the architecture for Arduino |  | 2016-06-01 | 2016-06-23 | 17 | Plan | 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0; 2016-06-18: 0; 2016-06-19: 0; 2016-06-20: 0; 2016-06-21: 0; 2016-06-22: 0; 2016-06-23: 0
| Implementation | Implement the architecture for context server. |  | 2016-06-01 | 2016-06-23 | 17 | Plan | 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0; 2016-06-18: 0; 2016-06-19: 0; 2016-06-20: 0; 2016-06-21: 0; 2016-06-22: 0; 2016-06-23: 0
| Implementation | Implement the DB schema |  | 2016-06-01 | 2016-06-23 | 17 | Plan | 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0; 2016-06-18: 0; 2016-06-19: 0; 2016-06-20: 0; 2016-06-21: 0; 2016-06-22: 0; 2016-06-23: 0
| Implementation | Implement the back-end web framework. |  | 2016-06-01 | 2016-06-23 | 17 | Plan | 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0; 2016-06-18: 0; 2016-06-19: 0; 2016-06-20: 0; 2016-06-21: 0; 2016-06-22: 0; 2016-06-23: 0
| Implementation | Implement the front-end web service. |  | 2016-06-01 | 2016-06-23 | 17 | Plan | 2016-06-01: 0; 2016-06-02: 0; 2016-06-03: 0; 2016-06-04: 0; 2016-06-05: 0; 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0; 2016-06-18: 0; 2016-06-19: 0; 2016-06-20: 0; 2016-06-21: 0; 2016-06-22: 0; 2016-06-23: 0
| Testing | Run unit test |  | 2016-06-06 | 2016-06-23 | 14 | Plan | 2016-06-06: 0; 2016-06-07: 0; 2016-06-08: 0; 2016-06-09: 0; 2016-06-10: 0; 2016-06-11: 0; 2016-06-12: 0; 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0; 2016-06-18: 0; 2016-06-19: 0; 2016-06-20: 0; 2016-06-21: 0; 2016-06-22: 0; 2016-06-23: 0
| Testing | Run integration test |  | 2016-06-13 | 2016-06-23 | 9 | Plan | 2016-06-13: 0; 2016-06-14: 0; 2016-06-15: 0; 2016-06-16: 0; 2016-06-17: 0; 2016-06-18: 0; 2016-06-19: 0; 2016-06-20: 0; 2016-06-21: 0; 2016-06-22: 0; 2016-06-23: 0
0
0
0
0
0
0
0
0
0
0
0